Attachment 2

Task List of the *Implementation Plan for Promoting the Standardized Construction and High-Quality Development of Village Clinics in Hainan Province*

|  |  |  |  |
| --- | --- | --- | --- |
| Number | Task  | Accountability Unit | Deadline |
|  | 2023  |  |  |
| 1 | Cities and counties should formulate and issue the *Implementation Plan for the Adjustment of village clinic Planning* and the *Standardized Construction Plan for Village Clinics*, complete the adjustment, propose a task list and project list for the standardized construction of village clinics, and report them to the Provincial Health Commission for filing. | Municipal and county people's governments | August 2023 |
| 2 | The Provincial Health Commission should formulate and issue the *Hainan Province Mechanism Plan for Village Clinic Star-Rating and Management*, carry out the star-rating management of village clinics, and achieve a coverage rate of over 50%. | Provincial Health Commission | December 2023 |
| 3 | Based on the standardized construction project list of village clinics at the municipal and county levels, related organs should improve the functional layout of village clinics in public ownership with a business area of 60 square meters, set up four rooms, adhere to the principle of "filling gaps and remedying deficiencies," and to ensure the supply of the basic devices, essential drugs, basic instruments, and basic office equipment (computers, printers, etc.). | Provincial Health Commission and municipal and county people's governments | December 2023 |
| 4 | According to the standardized construction project list of village clinics at the municipal and county levels, related organs should initiate a batch of standardized construction projects for village clinics whose business areas do not meet the standards or the ones that is not in public ownership. | Provincial Health Commission and municipal and county people's governments | December 2023 |
| 5 | Related organs should initiate rural integrated reform across the board, implement unified management of six aspects for village clinics by township health centers within their jurisdictions. | Provincial Health Commission and municipal and county people's governments | December 2023 |

|  |  |  |  |
| --- | --- | --- | --- |
| Number | Task | Accountability Unit |  Deadline |
| 6 | Related organs should print and issue the *Performance Assessment Plan for Grassroots Medical and Health Institutions in Hainan Province*, highlight health management effectiveness indicators for key groups and resident satisfaction as important criteria for village clinics’ performance assessment and their high-quality development. These indicators are also considered important references for fund allocation. | Hainan Provincial Health Commission, Provincial Finance Department, and municipal and county people's governments | December 2023 |
| 7 | Related organs should implement a special program for rural doctors selecting from university graduates, employ a group of recent graduates (including those who have not secured employment during the career choice period) with junior college diploma or above, majoring in medicine, to work in village clinics. | Provincial Health Commission and municipal and county people's governments | Keep progressing |
| 8 | Efforts should be made to raise the education levels of rural doctors, and at least 350 rural doctors who graduated from specialized secondary schools under the age of 50 should be selected to receive higher continuing education at Hainan Medical University or Hainan Health Vocational College. | Provincial Health Commission, Provincial Education Department, and municipal and county people's governments | Keep progressing |
| 9 | Support should be provided to Hainan Health Vocational College in offering clinical medicine or general practice courses for rural doctors, in order to cultivate qualified medical talent for village clinics. | Provincial Health Commission, Provincial Education Department | December 2023 |
| 10 | Efforts should be made to conduct the rural revitalization village doctor training project, and cultivate every year at least 180 young rural doctors with strong skills who are willing to work at the grassroots level. | Provincial Health Commission, Provincial Education Department, and municipal and county people's governments | Keep progressing |
| 11 | Efforts should be made to implement the plan for enhancing rural doctor service capacity, and allow a group of village doctors to receive free training at medical institutions affiliated to municipal or county-level administration or qualified township central health centers twice a year. The total training duration should not be less than 2 weeks. | Provincial Health Commission and municipal and county people's governments | Keep progressing |
| 12 | Staff in village clinics should be employed according to the principle of "admission by township and working for village," sign labor contracts, and will also be covered by the social security system. | Provincial Health Commission and municipal and county people's governments | Keep progressing |

|  |  |  |  |
| --- | --- | --- | --- |
| Number | Task | Accountability Unit | Deadline |
| 13 | Village clinics should be covered by medical liability insurance. | Provincial Health Commission, and municipal and county people's governments | Keep progressing |
| 14 | There should be a public health committee under the relevant village committee in all related regions and public health committees should fully play their roles.. | Provincial Civil Affairs Department, Provincial Health Commission, and municipal and county people's governments | December 2023 |
| 15 | Village clinics meeting relevant requirements should be listed in the designated medical institutions covered by medical insurance. | Provincial Healthcare Security Administration, Provincial Health Commission, and municipal and county people's governments | December 2023 |
| 16 | I窗体底端Medical services relating to TCM herbal decoction pieces and appropriate skills should be covered by medical insurance in village clinics, including acupuncture, massage, cupping, and moxibustion. | Provincial Healthcare Security Administration, Provincial Health Commission, and municipal and county people's governments | December 2023 |
| 17 | Efforts should be made to gradually increase the annual payment standards for outpatient services covered by medical insurance for urban and rural residents, to appropriately raise the reimbursement by village clinics, to support the development of the family doctor contract service mechanism, and to formulate policies on medical insurance payment and pricing to support the development of village clinics.  | Provincial Healthcare Security Administration, Provincial Health Commission, and municipal and county people's governments | December 2023 |
| 18 | Supporting services of outpatient drugs should be available for patients with hypertension or diabetes in village clinics.  | Provincial Healthcare Security Administration, Provincial Health Commission, and municipal and county people's governments | December 2023 |
| 19 | Efforts should be made to establish a mechanism to coordinate the supply of drugs within close medical consortia, and village clinics are allowed to be equipped and use non-essential drugs that count for less than 20% of total drugs | Provincial Healthcare Security Administration, Provincial Health Commission, and municipal and county people's governments | December 2023 |
| 20 | Village clinics should be equipped with intelligent assistance systems for diagnosis. | Provincial Health Commission, and municipal and county people's governments | Keep progressing |
| 21 | Efforts should be made to create integrated application terminals and information systems for village clinics, to achieve real-time information sharing, and to ensure health records will be updated timely and be accessible to residents. | Provincial Health Commission, Provincial Healthcare Security Administration, and municipal and county people's governments | December 2023 |

|  |  |  |  |
| --- | --- | --- | --- |
| Number | Task | Accountability Unit | Deadline |
|  | 2024  |  |  |
| 1 | Efforts should be made to carry out the star-rating management of village clinics, and achieve a coverage rate of over 80%. | Provincial Health Commission, and municipal and county people's governments | December 2024 |
| 2 | Based on the standardized construction project list of village clinics at the municipal and county levels, related organs should build new village clinics, and renovate or expand the ones that are not in public ownership with business areas less than 60 square meters. Additionally, efforts should be made to ensure the supply of basic devices, essential drugs, basic instruments, and basic office equipment (computers, printers, etc.); and to ensure that over 90% of village clinics are in public ownership. | Provincial Health Commission, and municipal and county people's governments | December 2024 |
| 3 | Efforts should be made to implement unified management of six aspects for all village clinics by township health centers within their jurisdictions | Provincial Health Commission, and municipal and county people's governments | December 2024 |
| 4 | Related organs should implement a special program for rural doctors selecting from university graduates, and employ a group of recent graduates (including those who have not secured employment during the career choice period) with junior college diplomas or above, majoring in medicine, to work in village clinics. | Provincial Health Commission, and municipal and county people's governments | Keep progressing |
| 5 | Efforts should be made to raise the education levels of rural doctors, and at least 350 rural doctors who graduated from specialized secondary schools under the age of 50 should be selected to receive higher continuing education at Hainan Medical University or Hainan Health Vocational College. | Provincial Health Commission, Provincial Education Department, and municipal and county people's governments | Keep progressing |
| 6 | Efforts should be made to conduct the rural revitalization village doctor training project, and cultivate every year at least 180 young rural doctors with strong skills who are willing to work at the grassroots level. | Provincial Health Commission, Provincial Education Department, and municipal and county people's governments | Keep progressing |
| 7 | Efforts should be made to implement the plan for enhancing rural doctor service capacity, and allow a group of village doctors to receive free training at medical institutions affiliated to municipal or county-level administration or qualified township central health centers twice a year. The total training duration should not be less than 2 weeks. | Provincial Health Commission, Provincial Education Department, and municipal and county people's governments | Keep progressing |
| 8 | Staff in village clinics should be employed according to the principle of "admission by township and working for village," sign labor contracts, and will also be covered by the social security system. | Provincial Health Commission, and municipal and county people's governments | December 2024 |

|  |  |  |  |
| --- | --- | --- | --- |
| Number | Task | Accountability Unit | Deadline |
| 9 | Village clinics should be covered by medical liability insurance. | Provincial Health Commission, and municipal and county people's governments. | December 2024 |
| 10 | Village clinics should be equipped with intelligent assistance systems for diagnosis. | Provincial Health Commission, and municipal and county people's governments. | December 2024 |
|  | 2025  |  |  |
| 1 | More efforts should be made to ensure the supply of basic devices, essential drugs, basic instruments, and basic office equipment (computers, printers, etc.) | Provincial Health Commission, and municipal and county people's governments. | December 2025 |
| 2 | All of the village clinics should be covered by star-rating assessment and management. | Provincial Health Commission, and municipal and county people's governments. | December 2025 |
| 3 | Related organs should implement the special program for rural doctors selected from university graduates, and employ a group of recent graduates (including those who have not secured employment during the career choice period) with junior college diplomas or above, majoring in medicine, to work in village clinics. | Provincial Health Commission, and municipal and county people's governments. | Keep progressing |
| 4 | Efforts should be made to raise the education levels of rural doctors, and at least 350 rural doctors who graduated from specialized secondary schools under the age of 50 should be selected to receive higher continuing education at Hainan Medical University or Hainan Health Vocational College. | Provincial Health Commission, Provincial Education Department, and municipal and county people's governments. | Keep progressing |
| 5 | Efforts should be made to conduct the rural revitalization village doctor training project, and cultivate every year at least 180 young rural doctors with strong skills who are willing to work at the grassroots level. | Provincial Health Commission, Provincial Education Department, and municipal and county people's governments. | Keep progressing |
| 6 | Efforts should be made to implement the plan for enhancing rural doctor service capacity, and allow a group of village doctors to receive free training at medical institutions affiliated to municipal or county-level administration or qualified township central health centers twice a year. The total training duration should not be less than 2 weeks. The training for all rural doctors across the province should be completed within 3 years. | Provincial Health Commission, Provincial Education Department, and municipal and county people's governments. | Keep progressing |
| 7 | Related organs should organize and conduct assessments and inspections. | Provincial Health Commission, and municipal and county people's governments. | December 2025 |

The General Office of the People's Government of Hainan Province

Issued on August 10, 2023.